## Change order
Change order
Describe the change, price it, and show its effect on the contract sum and time.
Change order number
Project
Contract
Date
Originated by (owner, architect, field condition...)
Reference (RFI, directive, bulletin)
Description of the change
Reason
Item | Quantity | Unit | Labor $ | Material $ | Equipment $ | Subcontract $ | Line total $
Subtotal
Overhead (%)
Profit (%)
Bond (%)
Total of this change
Contract sum and time
Original contract sum
Net change by previous change orders
Contract sum before this change
This change
New contract sum
Contract time change (days, + or -)
New substantial completion date
Agreed by (name, signature, date)
Contractor
Architect / engineer
Owner

## Change order log
Change order log
The running contract sum moves with approved changes only.
Original contract sum:
CO no. | Date | Description | Reference | Status | Amount requested $ | Amount approved $ | Days | Running contract sum $

## Instructions
How to use this change order template
1. Describe the change and what originated it: an owner request, an architect's bulletin, an RFI answer, a field condition. Reference the document.
2. Price it line by line (labor, material, equipment, subcontract), then apply your overhead, profit and bond rates as your contract allows.
3. Show its effect on the contract sum and on the contract time. Have it agreed and signed before the work proceeds, as your contract requires.
4. Record every change order in the log. The running contract sum moves with approved amounts only.
This template is a generic working document. It does not reproduce any standard form (such as the AIA G701), and your contract decides which form and which markups apply.
Mirage's agents tie each change back to the drawings, specification clauses and quantities that created it: miragemetrics.com/construction/change-orders
Mirage Metrics free template, miragemetrics.com/tools. Free to use and adapt.