## Punch list
Punch list
One row per deficiency. Days open and the summary sheet compute themselves.
Project
Area / phase
Walk date
Prepared by
Item no. | Location / room | Trade | Description of deficiency | Responsible (sub) | Date identified | Due date | Priority | Status | Date completed | Verified by | Date verified | Days open | Photo ref. | Notes
1 | Level 2, room 214 | Painting | Scuffed paint on north wall, touch up to match | Apex Painting | 2026-10-01 | 2026-10-08 | Low | Completed | 2026-10-06 |  |  |  | P-0214-01 | Example row: delete it.
Formulas:
Days open = IF([Date identified]="","",IF([Date completed]<>"",[Date completed]-[Date identified],TODAY()-[Date identified]))

## Summary
Punch list summary
Counts by status and by trade, from the Punch list sheet.
Status | Items
Open
Completed
Verified
Disputed
Void
Total
Open and past due
Trade | Open | Completed | Verified
Painting

## Instructions
How to use this punch list template
1. Fill the project block: project, area or phase walked, the walk date and who prepared the list.
2. One row per deficiency: a sequential number, the exact location, the trade, a description precise enough for the subcontractor to fix it without a call, who is responsible, the date identified and the due date.
3. Status moves from Open to Completed (the subcontractor says it is done) to Verified (your team or the architect checked it). Only Verified closes an item.
4. Days open compute from the date identified to the date completed, or to today. Open items past their due date turn red.
5. The Summary sheet counts items by status and, for the trades you type in column A, by trade.
The first row is a filled example: delete it. Mirage's agents read site photos and reports and tie each deficiency to its location on the drawings: miragemetrics.com/construction/progress-tracking
Mirage Metrics free template, miragemetrics.com/tools. Free to use and adapt.