## Schedule of values
Schedule of values and payment application
A generic continuation sheet: work completed, stored materials, retainage and the payment due. Not a standard form.
Project
Contractor
Application no.
Period to
Retainage rate (work) | 10%
Retainage rate (stored materials) | 10%
Item no. | Description of work | Scheduled value | From previous applications | This period | Materials presently stored | Total completed and stored to date | % complete | Balance to finish | Retainage
03 30 00 | Cast-in-place concrete | 450000 | 180000 | 90000 | 15000
Totals

## Application
Application for payment
Summary computed from the Schedule of values sheet and the contract figures you enter.
Original contract sum
Net change by change orders
Less previous certificates for payment
Contract sum to date
Total completed and stored to date
Retainage
Total earned less retainage
Less previous certificates for payment
Current payment due
Balance to finish, including retainage
Check: the schedule of values total should equal the contract sum to date.

## Instructions
How to use this schedule of values template
1. Fill the header, the retainage rates your contract sets (work and stored materials can differ) and the period covered.
2. Break the contract sum into line items with a scheduled value each; the lines should add up to the contract sum to date (the Application sheet checks it).
3. Each period, enter the value completed this period and the materials presently stored for each line; the amount from previous applications is last month's total completed and stored.
4. Total completed and stored, percent complete, balance to finish and retainage compute per line; a line billed above its scheduled value turns red.
5. The Application sheet takes the totals, your contract sum, change orders and previous certificates, and computes the current payment due.
This is a generic working document. It does not reproduce any standard form; the owner's contract decides which form is submitted and how retainage is held.
The first row is a filled example: delete it. Mirage's agents build the continuation sheet from the schedule of values and the progress records: miragemetrics.com/construction/pay-applications
Mirage Metrics free template, miragemetrics.com/tools. Free to use and adapt.